## Slide 1
Sprint 2 Review
Nguyễn Thiên Hương

## Slide 2: Plan
Sprint 2 Review
The work the team completed
The work the team not-completed
Strengths
Weakness
Threats
Difficulty for our project

## Slide 3: Tasks in Sprint 2
Sprint 2 Review
Plan Purchasing Management
BoM Management
PO Management
Logistics Management
Upload/Import files
Product Management
Inventory Management (version 1)
Test functions for Sprint 1

## Slide 4: The work the team completed
Sprint 2 Review
Plan Purchasing Management
BoM Management
PO Management
Logistics Management
Upload/Import files
Product Management
Inventory Management (version 1)
Test functions for Sprint 1

## Slide 5: The work the team not-completed
Sprint 2 Review
BoM Management
  Negotiate
PO Management
  Link to BoM Management
Logistics Management
  Upload files
  Edit detail
Test functions for Sprint 1
  Missing functional test cases

## Slide 6: Strengths
Sprint 2 Review
  Team members are very hard-working to finish his tasks.
  Quickly adapt with new technology (AngularJS, Laravel frameworks)
  Smoothly with GIT

## Slide 7: Weakness
Sprint 2 Review
  Testers is pretty new, they have not enough experiences & need support from other to finish their tasks
  Collaborate on jira and team members

## Slide 8: Threats
Sprint 2 Review
  QuangHX has family’s stuff so his assigned tasks must delay in the next sprint . All members are overloading with the short planning

## Slide 9: Difficulty
Sprint 2 Review
  The plan to finish the project is very short, so all members must spend the best of their efforts & work overtime to be sure the assigned tasks are finished by the deadline.
  Requirements change so quickly, not clear at the beginning
  No resource for reviewing source code: Human & time
  No UI designers

## Slide 10: Improve for Sprint 3
Sprint 2 Review
Review tasks assigned tasks & all functions before coding
Any change about requirements must discuss with BA
More collaborate with other team members on JIRA(comment)
Lan/Hương will review functional before merging to develop branch
Raise to leaders(Hương/Hải) when meeting problems of tasks or deadline before the date of ending Sprint

## Slide 11
Cảm ơn!
Nguyễn Thiên Hương