## Sheet1
Sprint 2 | 08 - 21 March
10days
Name | Task | %Done | General Evaluation | No of Planned Days | No of Logged Days
Nguyễn Minh Tiến | SSDC_ERP-136 | 100 |  | 1d | 0
| SSDC_ERP-137 | 100 |  | 1d | 1d
| SSDC_ERP-138 | Cancelled |  | 1d
| SSDC_ERP-139 | 100 |  | 1d | 0
| SSDC_ERP-133 | 100 |  | 2d | 2d
| SSDC_ERP-134 | 100 |  | 1d | 3d
| SSDC_ERP-135 | 100 |  | 1d | 1d
| SSDC_ERP-149 | 100 |  | 1d | 1d
| SSDC_ERP-126 | 100 |  | 1d | 1d
|  |  |  | 10d | 9d
Hoàng Xuân Quang
| SSDC_ERP-144 |  |  | 1w | 3d
| SSDC_ERP-91 | 100 | Ok | 3d | 3d2h
| SSDC_ERP-126 | 100 |  | 1d | 1d
|  |  |  | 9d | 7d2h
Nguyễn Thiên Hương | SSDC_ERP-147 | 100 |  | 1d | 1d
| SSDC_ERP-170 | 100 |  | 4d | 1d
| SSDC_ERP-175 | 100 |  | 3d | 2d
| SSDC_ERP-126 | 100 |  | 1d | 1d
|  |  |  | 9d | 5d
Nguyễn Thị Lan | SSDC_ERP-168 | 100 | Ok | 1d | 1d
| SSDC_ERP-122 | 100 |  | 1d4h | 1d4h
| SSDC_ERP-150 | 100 |  | 2d | 1d4h
| SSDC_ERP-151 | 100 |  | 1d | 1d
| SSDC_ERP-152 | 100 |  | 1d4h | 4h
| SSDC_ERP-153 | 100 |  | 1d4h | 4h
| SSDC_ERP-155 | 100 |  | 2d | 2d4h
| SSDC_ERP-125 | 100 |  | 4h | 4h
| SSDC_ERP-160 | 100 | Ok | 4h | 4h
| SSDC_ERP-172 | 100 | Ok | 1d | 1d
| SSDC_ERP-126 | 100 |  | 1d | 4h
|  |  |  | 13d4h | 11d | Làm bù 1 ngày thứ 7
Đinh Hoàng Hải | SSDC_ERP-142 | 50 | Pending | 2d | 1d
| SSDC_ERP-119 |  |  | 2d | 2d
|  |  |  | 4d | 3d
Nguyễn Mạnh Tuấn | SSDC_ERP-120 | 100 |  | 3d | 3d
| SSDC_ERP-164 | 100 |  | 4d4h | 2d
|  |  |  | 7d4h | 5d
Nguyễn Văn Lương | SSDC_ERP-127 | 100 |  | 1d | 1d
| SSDC_ERP-128 | 100 |  | 1d | 3d
| SSDC_ERP-129 | 100 |  | 1d | 7h
| SSDC_ERP-130 | 100 |  | 1d | 7h
| SSDC_ERP-126 | 100 |  | 1d | 1d
| SSDC_ERP-144 |  |  | 1w | 4d2h
|  |  |  | 10d | 11d
Lê Văn Thuyết | SSDC_ERP-140 | 100 |  | 2d | 3d
| SSDC_ERP-141 | 100 |  | 2d | 0
| SSDC_ERP-126 | 100 |  | 1d | 1d
| SSDC_ERP-131 | 100 |  | 2d | 2d
| SSDC_ERP-132 | 100 |  | 2d | 3d
|  |  |  | 9d | 9d
Hoàng Văn Bảo | SSDC_ERP-145 | 100 |  | 1w | 1w4d
|  |  |  | 5d | 9d
36 tasks